## Commissioning Cals
Commissioning Calibrations: | Details | Responsible for looking at data (within 24 hours) | Final outcome | Day (estimated based on current schedule)
light leak (with doors closed) | *** Modify esp, megs_a and megs_b comm procedures. During filter wheel movements dwell at each filter (ESP 5 seconds; MEGS A 40 seconds except for primary - 15 minutes; MEGS B 40 seconds; SAM 40 seconds) |  |  | L+33
filter edge sweep (coarse) | each filter edge |  |  | L+35 (load on L+33)
dark for a couple of hours | couple hours of dark early after door openings. Following filter edge sweep |  |  | L+35 (load on L+33)
filter scan (fine) | MEGS A in dark, step through SAM filters SAM in dark, step through MEGS A filters |  | each filter nominal step is defined (update in OASIS-CC). Verify SAM does not corrupt MEGS A | L+36 to L+37 (load on day L+36)
CCD Taps | change filters for each tap combo |  |  | L+40 (load L+39)
glint scan | MEGS A solar data, SAM in dark - need to analyze data to determine if a special test needs to be performed. |  |  | L+41 (load L+40)
2nd order cal | expose MEGS A and B second order filters for 15 minutes (SAM in dark); combined with MEGS A glint
Temperature calibrations | (esp and ccds), dark, gain, cal |  |  | after L+44 as available
led calibrations | flatfields at different levels; combined with temp cals |  |  | -
diode cals | stay in calibration mode for 15 minutes; combined with temp cals |  |  | -
esp hv on/off over an orbit | combined with temperature calibrations |  |  | -
dark for a day | Solar spectrum for 15 minutes, run the daily cal, and then begin the day of dark |  |  | L+60
OASIS-PS generated daily cal | chance to see if this is what we want or if it needs tweeked; combined with dark for a day |  |  | -
SAM solar aspect for a whole day | after fine pointing (may be done after day 60). |  |  | Following Temperature calibrations as available
eclipse SAM test | as we come out of eclipse, SAM in solar aspect mode (pos2) to measure temp effect on the apperature |  |  | Target of opportunity based on eclipse

## Filter edge sweep
Filter Edge Sweep (Coarse) | CSTOL procedure | filter_edge | Notes
ESP: 1. Find home 2. loop 400: move 3 steps; wait 3 seconds 3. finish in dark | Time from previous command (in seconds) | Command
MEGS B: 1. Find home 2. loop 400: move 3 steps; wait 3 seconds 3. finish in dark | 0 | find esp fltrwhlhome
MEGS A: 1. SAM in dark 2. Find home 3. loop 400: move 3 steps; wait 3 seconds 4. finish in dark | Loop 400 | step esp fltrwhl with steps 3; wait 00:00:03 | move an entire revolution, 3 steps at a time, waiting 3 seconds between movements
SAM: 1. MEGS A in dark 2. Find home 3. loop 1200: move 1 step; wait 3 seconds 4. finish in dark | 1 | move esp fltrwhl to dark | End ESP filter in dark
| 1 | find megs_b fltrwhlhome
NOTE: Remain in dark at end of this experiment (until the find filter scan experiment). This will cover the "dark for a couple of hours" experiment. | Loop 400 | step megs_b fltrwhl with steps 3; wait 00:00:03 | move an entire revolution, 3 steps at a time, waiting 3 seconds between movements
| 1 | move megs_b fltrwhl to dark | End megs_b filter in dark
| 1 | move sam fltrwhl to dark
| 1 | find megs_a fltrwhlhome
| Loop 400 | step megs_a fltrwhl with steps 3; wait 00:00:03 | move an entire revolution, 3 steps at a time, waiting 3 seconds between movements
| 1 | move megs_a fltrwhl to dark | End megs_a filter in dark
| 1 | find sam fltrwhlhome
| Loop 400 | step sam fltrwhl with steps 3; wait 00:00:03 | move an entire revolution, 3 steps at a time, waiting 3 seconds between movements
| 1 | move sam fltrwhl to dark | End sam filter in dark

## Filter scan
Filter scan (fine) | Filter | start | end | center | step # | Start step # | CSTOL procedure | filter_scan_esp | Notes
ESP: 1 step dwell for 3 seconds; 100 steps over pos 2,3,4,5 center points finish in dark | ESP 2 | 13352 | 16516 | 14934 | 273.4539 | 223.4539 | Time from previous command (in seconds) | Command
| ESP 3 | 26688 | 29720 | 28204 | 516.4385 | 466.4385 | 0 | step esp fltrwhl with steps 223, mode abs | ESP filter 2 (50 steps before center)
MEGS A: (SAM in dark) 1 step dwell for 30 seconds; 100 steps over pos 2,3,4,5 center points finish in dark | ESP 4 | 39628 | 42616 | 41122 | 752.9778 | 702.9778 | Loop 100 | step esp fltrwhl with steps 1; wait 00:00:03 | move over filter 2, 1 step at a time, waiting 3 seconds between movements
SAM: (MEGS A in dark) 1 step dwell for 30 seconds; 100 steps over pos 2,3,4,5 center points finish in dark | ESP 5 | 53849 | 54285 | 54067 | 990.0114 | 940.0114 | 1 | step esp fltrwhl with steps 466, mode abs | ESP filter 3 (50 steps before center)
MEGS B: 1 step dwell for 30 seconds; 100 steps over pos 2,3,4,5 center points finish in dark | MEGS A 2 | 14124 | 15768 | 14946 | 273.6736 | 223.6736 | Loop 100 | step esp fltrwhl with steps 1; wait 00:00:03 | move over filter 3, 1 step at a time, waiting 3 seconds between movements
| MEGS A 3 | 27466 | 28953 | 28209.5 | 516.5393 | 466.5393 | 1 | step esp fltrwhl with steps 702, mode abs | ESP filter 4 (50 steps before center)
Note: Before s/c cal maneuvers (one of first things we do). PRIOR to running this procedure, use the data from the filter edge sweep to confirm start (based on center) steps. | MEGS A 4 | 40384 | 41969 | 41176.5 | 753.9757 | 703.9757 | Loop 100 | step esp fltrwhl with steps 1; wait 00:00:03 | move over filter 4, 1 step at a time, waiting 3 seconds between movements
| MEGS A 5 | 53826 | 59049 | 56437.5 | 1033.4173 | 983.4173 | 1 | step esp fltrwhl with steps 940, mode abs | ESP filter 5 (50 steps before center)
| SAM 2 | 12308 | 17937 | 15122.5 | 276.9055 | 226.9055 | Loop 100 | step esp fltrwhl with steps 1; wait 00:00:03 | move over filter 5, 1 step at a time, waiting 3 seconds between movements
| SAM 3 | 27030 | 29602 | 28316 | 518.4894 | 468.4894 | 1 | move esp fltrwhl to dark | Finish in dark
| SAM 4 | 39972 | 42813 | 41392.5 | 757.9309 | 707.9309
| SAM 5 | 51728 | 57321 | 54524.5 | 998.3886 | 948.3886
| MEGS B 2 | 14133 | 15875 | 15004 | 274.7356 | 224.7356
| MEGS B 3 | 25093 | 31253 | 28173 | 515.8709 | 465.8709
| MEGS B 4 | 40960 | 41396 | 41178 | 754.0032 | 704.0032
| MEGS B 5 | 51928 | 56728 | 54328 | 994.7906 | 944.7906 | CSTOL procedure | filter_scan_ma | Notes
[7 empty] | Time from previous command (in seconds) | Command
[7 empty] | 0 | move sam fltrwhl to dark | SAM in dark for this test
[7 empty] | 1 | step megs_a fltrwhl with steps 223, mode abs | megs_a filter 2 (50 steps before center)
[7 empty] | Loop 100 | step megs_a fltrwhl with steps 1; wait 00:00:30 | move over filter 2, 1 step at a time, waiting 30 seconds between movements
[7 empty] | 1 | step megs_a fltrwhl with steps 466, mode abs | megs_a filter 3 (50 steps before center)
[7 empty] | Loop 100 | step megs_a fltrwhl with steps 1; wait 00:00:30 | move over filter 3, 1 step at a time, waiting 30 seconds between movements
[7 empty] | 1 | step megs_a fltrwhl with steps 703, mode abs | megs_a filter 4 (50 steps before center)
[7 empty] | Loop 100 | step megs_a fltrwhl with steps 1; wait 00:00:30 | move over filter 4, 1 step at a time, waiting 30 seconds between movements
[7 empty] | 1 | step megs_a fltrwhl with steps 983, mode abs | megs_a filter 5 (50 steps before center)
[7 empty] | Loop 100 | step megs_a fltrwhl with steps 1; wait 00:00:30 | move over filter 5, 1 step at a time, waiting 30 seconds between movements
[7 empty] | 1 | move megs_a fltrwhl to dark | Finish in dark
[7 empty] | CSTOL procedure | filter_scan_sam | Notes
[7 empty] | Time from previous command (in seconds) | Command
[7 empty] | 0 | move megs_a fltrwhl to dark | MEGS A in dark for this test
[7 empty] | 1 | step sam fltrwhl with steps 223, mode abs | sam filter 2 (50 steps before center)
[7 empty] | Loop 100 | step sam fltrwhl with steps 1; wait 00:00:30 | move over filter 2, 1 step at a time, waiting 30 seconds between movements
[7 empty] | 1 | step sam fltrwhl with steps 466, mode abs | sam filter 3 (50 steps before center)
[7 empty] | Loop 100 | step sam fltrwhl with steps 1; wait 00:00:30 | move over filter 3, 1 step at a time, waiting 30 seconds between movements
[7 empty] | 1 | step sam fltrwhl with steps 703, mode abs | sam filter 4 (50 steps before center)
[7 empty] | Loop 100 | step sam fltrwhl with steps 1; wait 00:00:30 | move over filter 4, 1 step at a time, waiting 30 seconds between movements
[7 empty] | 1 | step sam fltrwhl with steps 983, mode abs | sam filter 5 (50 steps before center)
[7 empty] | Loop 100 | step sam fltrwhl with steps 1; wait 00:00:30 | move over filter 5, 1 step at a time, waiting 30 seconds between movements
[7 empty] | 1 | move sam fltrwhl to dark | Finish in dark
[7 empty] | CSTOL procedure | filter_scan_mb | Notes
[7 empty] | Time from previous command (in seconds) | Command
[7 empty] | 1 | step megs_b fltrwhl with steps 223, mode abs | megs_b filter 2 (50 steps before center)
[7 empty] | Loop 100 | step megs_b fltrwhl with steps 1; wait 00:00:30 | move over filter 2, 1 step at a time, waiting 30 seconds between movements
[7 empty] | 1 | step megs_b fltrwhl with steps 466, mode abs | megs_b filter 3 (50 steps before center)
[7 empty] | Loop 100 | step megs_b fltrwhl with steps 1; wait 00:00:30 | move over filter 3, 1 step at a time, waiting 30 seconds between movements
[7 empty] | 1 | step megs_b fltrwhl with steps 703, mode abs | megs_b filter 4 (50 steps before center)
[7 empty] | Loop 100 | step megs_b fltrwhl with steps 1; wait 00:00:30 | move over filter 4, 1 step at a time, waiting 30 seconds between movements
[7 empty] | 1 | step megs_b fltrwhl with steps 983, mode abs | megs_b filter 5 (50 steps before center)
[7 empty] | Loop 100 | step megs_b fltrwhl with steps 1; wait 00:00:30 | move over filter 5, 1 step at a time, waiting 30 seconds between movements
[7 empty] | 1 | move megs_b fltrwhl to dark | Finish in dark

## CCD Taps
CCD Taps | CSTOL procedure | ccd_taps | Notes
ESP in Science mode entire time 1. Nominal tap configuration a. Dark 30 minutes b. Primary science filters (MEGS A, MEGS B), SAM in pos 2; 15 minutes c. change to dark filters (no wait) d. LED nominal (daily cal - one color and level) 15 minutes 2. Change tap configuration repeat a-d 3. Change tap configuration repeat a-d 4. Change tap configuration repeat a-d 5. return to nominal tap config repeat a-d | Time from previous command (in seconds) | Command
| 0 | move esp fltrwhl to primary
NOTE: may be performed prior to fine pointing | 1 | disable esp cal_mode | ESP in nominal science mode (for entire experiment)
| 1 | set megs_a integration | Default taps (top left, bottom right)
| 1 | set megs_b integration | Default taps (top left, bottom left)
| 1 | move megs_a fltrwhl to dark
| 1 | move megs_b fltrwhl to dark
| 1 | move sam fltrwhl to dark
| 1800 | move megs_a fltrwhl to primary | dark for 30 minutes
| 1 | move megs_b fltrwhl to primary
| 1 | move sam fltrwhl to aspect
| 900 | move megs_a fltrwhl to dark | MEGS A, MEGS B in primary; SAM in pos 2; 15 minutes
| 1 | move megs_b fltrwhl to dark
| 1 | move sam fltrwhl to dark | MEGS A, B and SAM in dark
| 1 | turn on megs_a led with lamp blue, level 8
| 1 | turn on megs_b led with lamp blue, level 6
| 900 | turn off megs_a led from blue | MEGS A & B LED for 15 minutes
| 1 | turn off megs_b led from blue
| 1 | set megs_a integration with top_readout left, bottom_readout left | Change tap config (A: top left, bottom left. B: top left, bottom right)
| 1 | set megs_b integration with top_readout left, bottom_readout right
| 1800 | move megs_a fltrwhl to primary | dark for 30 minutes
| 1 | move megs_b fltrwhl to primary
| 1 | move sam fltrwhl to aspect
| 900 | move megs_a fltrwhl to dark | MEGS A, MEGS B in primary; SAM in pos 2; 15 minutes
| 1 | move megs_b fltrwhl to dark
| 1 | move sam fltrwhl to dark | MEGS A, B and SAM in dark
| 1 | turn on megs_a led with lamp blue, level 8
| 1 | turn on megs_b led with lamp blue, level 6
| 900 | turn off megs_a led from blue | MEGS A & B LED for 15 minutes
| 1 | turn off megs_b led from blue
| 1 | set megs_a integration with top_readout right, bottom_readout left | Change tap config (A: top right, bottom left. B: top right, bottom right)
| 1 | set megs_b integration with top_readout right, bottom_readout right
| 1800 | move megs_a fltrwhl to primary | dark for 30 minutes
| 1 | move megs_b fltrwhl to primary
| 1 | move sam fltrwhl to aspect
| 900 | move megs_a fltrwhl to dark | MEGS A, MEGS B in primary; SAM in pos 2; 15 minutes
| 1 | move megs_b fltrwhl to dark
| 1 | move sam fltrwhl to dark | MEGS A, B and SAM in dark
| 1 | turn on megs_a led with lamp blue, level 8
| 1 | turn on megs_b led with lamp blue, level 6
| 900 | turn off megs_a led from blue | MEGS A & B LED for 15 minutes
| 1 | turn off megs_b led from blue
| 1 | set megs_a integration with top_readout right, bottom_readout right | Change tap config (A: top right, bottom right. B: top right, bottom left)
| 1 | set megs_b integration with top_readout right, bottom_readout left
| 1800 | move megs_a fltrwhl to primary | dark for 30 minutes
| 1 | move megs_b fltrwhl to primary
| 1 | move sam fltrwhl to aspect
| 900 | move megs_a fltrwhl to dark | MEGS A, MEGS B in primary; SAM in pos 2; 15 minutes
| 1 | move megs_b fltrwhl to dark
| 1 | move sam fltrwhl to dark | MEGS A, B and SAM in dark
| 1 | turn on megs_a led with lamp blue, level 8
| 1 | turn on megs_b led with lamp blue, level 6
| 900 | turn off megs_a led from blue | MEGS A & B LED for 15 minutes
| 1 | turn off megs_b led from blue
| 1 | set megs_a integration with top_readout left, bottom_readout right | Change tap config (A: top left, bottom right. B: top left, bottom left)
| 1 | set megs_b integration with top_readout left, bottom_readout left
| 1800 | move megs_a fltrwhl to primary | dark for 30 minutes
| 1 | move megs_b fltrwhl to primary
| 1 | move sam fltrwhl to aspect
| 900 | move megs_a fltrwhl to dark | MEGS A, MEGS B in primary; SAM in pos 2; 15 minutes
| 1 | move megs_b fltrwhl to dark
| 1 | move sam fltrwhl to dark | MEGS A, B and SAM in dark
| 1 | turn on megs_a led with lamp blue, level 8
| 1 | turn on megs_b led with lamp blue, level 6
| 900 | turn off megs_a led from blue | MEGS A & B LED for 15 minutes
| 1 | turn off megs_b led from blue
| 1 | move megs_a fltrwhl to primary
| 1 | move megs_b fltrwhl to primary
| 1 | move sam fltrwhl to primary | return to nominal science mode

## Glint scan
Glint scan | CSTOL procedure | glint_scan | Notes
1. MEGS A primary; SAM in dark 2 hours 2. MEGS A second order, MEGS B second order, SAM in dark - 15 minutes 3. Return to normal science | Time from previous command (in seconds) | Command
| 0 | move sam fltrwhl to dark
NOTE: any time doors are open and before fine pointing | 1 | move megs_a fltrwhl to primary
| 7200 | move megs_a fltrwhl to second_order | MEGS A in primary, SAM in dark for 2 hours
| 1 | move megs_b fltrwhl to second_order
| 900 | move megs_a fltrwhl to primary | MEGS A, B in second order, SAM in dark for 15 minutes
| 1 | move megs_b fltrwhl to primary
| 1 | move sam fltrwhl to primary | Return MEGS A, B and SAM to primary filters

## Dark
Dark for a day | CSTOL procedure | glint_scan | Notes
Solar spectrum for 15 minutes, run the daily cal, and then begin the day of dark | Time from previous command (in seconds) | Command
| *** | Use OASIS-PS generated daily_cal for this day (then append the following) | OASIS-PS daily cal
NOTE: After fine pointing (as close to day 60 as possible) | 1 | move esp fltrwhl to dark
| 1 | move megs_a fltrwhl to dark
| 1 | move megs_b fltrwhl to dark
| 1 | move sam fltrwhl to dark
| 86400 | activate rts from 4 | after 24 hours of dark, return to normal science via the default science RTS

## Temperature calibrations (2)
Temperature calibrations | CSTOL procedure | temp_cal_day1 (CCDs -90, EOP 10) | Notes
CCD temperature -90,-95, -85, -90; (EOP at 10) 1. After temp stabalized: Dark (all filters) for 15 minutes 2. Remain in dark: Flatfields standard cal levels (2 per LED) for 15 minutes each for B, 30 minutes each for A; ESP and MEGS P in cal mode for 15 minutes 3. dark for 15 minutes 4. Primary science filters except for SAM (solar aspect pos 2), nominal integration, 15 minutes 5. dark for 15 minutes 6. change CCD temperature (remain in dark) | Time from previous command (in seconds) | Command
NOTES: Same time of day for each temperature; | 0 (Note, use same time of day for the start of this portion of the proc for all 7 experiments) | move esp fltrwhl to dark
NOTE: during the first -90 test, ESP HV off for entire day (30 minutes HV on, 30 minutes HV off. Alternating for 24 hours) | 1 | move megs_a fltrwhl to dark
| 1 | move megs_b fltrwhl to dark
| 1 | move sam fltrwhl to dark
EOP temperature 10, 5, 15, 10; (CCD at -90) 1. After temp stabalized: Dark (all filters) for 15 minutes 2. Remain in dark: Flatfields standard cal levels (2 per LED) for 15 minutes each for B, 30 minutes each for A; ESP and MEGS P in cal mode for 15 minutes 3. dark for 15 minutes 4. Primary science filters except for SAM (solar aspect pos 2), nominal integration, 15 minutes 5. dark for 15 minutes 6. change EOP temperature (remain in dark) | 900 | turn on megs_b led with lamp blue, level 3 | dark for 15 minutes
| 1 | turn on megs_a led with lamp blue, level 4
| 1 | enable esp cal_mode
after L+44 (fine pointing), this will take 7 days | 1 | enable megs_p cal_mode
| 900 | turn off megs_b led from blue | MEGS B LED, ESP and MEGS P in cal mode for 15 minutes
| 1 | turn on megs_b led with lamp blue, level 6
| 1 | disable esp cal_mode
| 1 | disable megs_p cal_mode
| 900 | turn off megs_b led from blue | MEGS B LED for 15 minutes; MEGS A LED for 30 minutes
| 1 | turn off megs_a led from blue
| 1 | turn on megs_b led with lamp violet level 3
| 1 | turn on megs_a led with lamp blue, level 8
| 900 | turn off megs_b led from violet | MEGS B LED for 15 minutes
| 1 | turn on megs_b led with lamp violet level 6
| 900 | turn off megs_b led from violet | MEGS B LED for 15 minutes; MEGS A LED for 30 minutes
| 1 | turn off megs_a led from blue
| 900 | move esp fltrwhl to primary | dark for 15 minutes
| 1 | move megs_a fltrwhl to primary
| 1 | move megs_b fltrwhl to primary
| 1 | move sam fltrwhl to aspect
| 900 | move esp fltrwhl to dark | Primary (except SAM) for 15 minutes
| 1 | move megs_a fltrwhl to dark
| 1 | move megs_b fltrwhl to dark
| 1 | move sam fltrwhl to dark
| LOOP: every 30 minutes | Toggle ESP HV (on/off) | Toggle ESP HV for remaining 22 hours
| 79200 | activate rts from 4 | dark for 22 hours; then trigger normal science mode. This is to allow for days between experiments (if necessary)
| 1 | TBD: set megs_a ccd_htr_trip to -85.0c (based on when next experiment occurs) | Remain in nominal (don't use this command) OR set CCD temp to temperature for next test.
| 1 | TBD: set megs_b ccd_htr_trip to -85.0c (based on when next experiment occurs) | Remain in nominal (don't use this command) OR set CCD temp to temperature for next test.
| CSTOL procedure | temp_cal_day2 (CCDs -95, EOP 10)
| Time from previous command (in seconds) | Command
| 0 | set megs_a ccd_htr_trip to -95.0c
| 1 | set megs_b ccd_htr_trip to -95.0c
| 86400 (Note, use same time of day for the start of this portion of the proc for all 7 experiments) | move esp fltrwhl to dark
| 1 | move megs_a fltrwhl to dark
| 1 | move megs_b fltrwhl to dark
| 1 | move sam fltrwhl to dark
| 900 | turn on megs_b led with lamp blue, level 3 | dark for 15 minutes
| 1 | turn on megs_a led with lamp blue, level 4
| 1 | enable esp cal_mode
| 1 | enable megs_p cal_mode
| 900 | turn off megs_b led from blue | MEGS B LED, ESP and MEGS P in cal mode for 15 minutes
| 1 | turn on megs_b led with lamp blue, level 6
| 1 | disable esp cal_mode
| 1 | disable megs_p cal_mode
| 900 | turn off megs_b led from blue | MEGS B LED for 15 minutes; MEGS A LED for 30 minutes
| 1 | turn off megs_a led from blue
| 1 | turn on megs_b led with lamp violet level 3
| 1 | turn on megs_a led with lamp blue, level 8
| 900 | turn off megs_b led from violet | MEGS B LED for 15 minutes
| 1 | turn on megs_b led with lamp violet level 6
| 900 | turn off megs_b led from violet | MEGS B LED for 15 minutes; MEGS A LED for 30 minutes
| 1 | turn off megs_a led from blue
| 900 | move esp fltrwhl to primary | dark for 15 minutes
| 1 | move megs_a fltrwhl to primary
| 1 | move megs_b fltrwhl to primary
| 1 | move sam fltrwhl to aspect
| 900 | move esp fltrwhl to dark | Primary (except SAM) for 15 minutes
| 1 | move megs_a fltrwhl to dark
| 1 | move megs_b fltrwhl to dark
| 1 | move sam fltrwhl to dark
| 79200 | activate rts from 4 | dark for 22 hours; then trigger normal science mode. This is to allow for days between experiments (if necessary)
| 1 | set megs_a ccd_htr_trip to TBD (based on when next experiment occurs) | set CCD temp back to nominal OR to temperature for next test.
| 1 | set megs_b ccd_htr_trip to TBD (based on when next experiment occurs) | set CCD temp back to nominal OR to temperature for next test.
| CSTOL procedure | temp_cal_day3 (CCDs -85, EOP 10)
| Time from previous command (in seconds) | Command
| 0 | set megs_a ccd_htr_trip to -85.0c
| 1 | set megs_b ccd_htr_trip to -85.0c
| 86400 (Note, use same time of day for the start of this portion of the proc for all 7 experiments) | move esp fltrwhl to dark
| 1 | move megs_a fltrwhl to dark
| 1 | move megs_b fltrwhl to dark
| 1 | move sam fltrwhl to dark
| 900 | turn on megs_b led with lamp blue, level 3 | dark for 15 minutes
| 1 | turn on megs_a led with lamp blue, level 4
| 1 | enable esp cal_mode
| 1 | enable megs_p cal_mode
| 900 | turn off megs_b led from blue | MEGS B LED, ESP and MEGS P in cal mode for 15 minutes
| 1 | turn on megs_b led with lamp blue, level 6
| 1 | disable esp cal_mode
| 1 | disable megs_p cal_mode
| 900 | turn off megs_b led from blue | MEGS B LED for 15 minutes; MEGS A LED for 30 minutes
| 1 | turn off megs_a led from blue
| 1 | turn on megs_b led with lamp violet level 3
| 1 | turn on megs_a led with lamp blue, level 8
| 900 | turn off megs_b led from violet | MEGS B LED for 15 minutes
| 1 | turn on megs_b led with lamp violet level 6
| 900 | turn off megs_b led from violet | MEGS B LED for 15 minutes; MEGS A LED for 30 minutes
| 1 | turn off megs_a led from blue
| 900 | move esp fltrwhl to primary | dark for 15 minutes
| 1 | move megs_a fltrwhl to primary
| 1 | move megs_b fltrwhl to primary
| 1 | move sam fltrwhl to aspect
| 900 | move esp fltrwhl to dark | Primary (except SAM) for 15 minutes
| 1 | move megs_a fltrwhl to dark
| 1 | move megs_b fltrwhl to dark
| 1 | move sam fltrwhl to dark
| 79200 | activate rts from 4 | dark for 22 hours; then trigger normal science mode. This is to allow for days between experiments (if necessary)
| 1 | set megs_a ccd_htr_trip to -90.0c | set CCD temp back to nominal
| 1 | set megs_b ccd_htr_trip to -90.0c | set CCD temp back to nominal
| CSTOL procedure | temp_cal_day4 (CCDs -90, EOP 10)
| Time from previous command (in seconds) | Command
| 0 (Note, use same time of day for the start of this portion of the proc for all 7 experiments) | move esp fltrwhl to dark
| 1 | move megs_a fltrwhl to dark
| 1 | move megs_b fltrwhl to dark
| 1 | move sam fltrwhl to dark
| 900 | turn on megs_b led with lamp blue, level 3 | dark for 15 minutes
| 1 | turn on megs_a led with lamp blue, level 4
| 1 | enable esp cal_mode
| 1 | enable megs_p cal_mode
| 900 | turn off megs_b led from blue | MEGS B LED, ESP and MEGS P in cal mode for 15 minutes
| 1 | turn on megs_b led with lamp blue, level 6
| 1 | disable esp cal_mode
| 1 | disable megs_p cal_mode
| 900 | turn off megs_b led from blue | MEGS B LED for 15 minutes; MEGS A LED for 30 minutes
| 1 | turn off megs_a led from blue
| 1 | turn on megs_b led with lamp violet level 3
| 1 | turn on megs_a led with lamp blue, level 8
| 900 | turn off megs_b led from violet | MEGS B LED for 15 minutes
| 1 | turn on megs_b led with lamp violet level 6
| 900 | turn off megs_b led from violet | MEGS B LED for 15 minutes; MEGS A LED for 30 minutes
| 1 | turn off megs_a led from blue
| 900 | move esp fltrwhl to primary | dark for 15 minutes
| 1 | move megs_a fltrwhl to primary
| 1 | move megs_b fltrwhl to primary
| 1 | move sam fltrwhl to aspect
| 900 | move esp fltrwhl to dark | Primary (except SAM) for 15 minutes
| 1 | move megs_a fltrwhl to dark
| 1 | move megs_b fltrwhl to dark
| 1 | move sam fltrwhl to dark
| 79200 | activate rts from 4 | dark for 22 hours; then trigger normal science mode. This is to allow for days between experiments (if necessary)
| 1 | TBD: set eop op_htr_trip to 5.0c (based on when next experiment occurs) | Remain in nominal (don't use this command) OR set EOP temp to temperature for next test.
| CSTOL procedure | temp_cal_day5 (CCDs -90, EOP 5)
| Time from previous command (in seconds) | Command
| 0 | set eop op_htr_trip to 5.0c
| 86400 (Note, use same time of day for the start of this portion of the proc for all 7 experiments) | move esp fltrwhl to dark
| 1 | move megs_a fltrwhl to dark
| 1 | move megs_b fltrwhl to dark
| 1 | move sam fltrwhl to dark
| 900 | turn on megs_b led with lamp blue, level 3 | dark for 15 minutes
| 1 | turn on megs_a led with lamp blue, level 4
| 1 | enable esp cal_mode
| 1 | enable megs_p cal_mode
| 900 | turn off megs_b led from blue | MEGS B LED, ESP and MEGS P in cal mode for 15 minutes
| 1 | turn on megs_b led with lamp blue, level 6
| 1 | disable esp cal_mode
| 1 | disable megs_p cal_mode
| 900 | turn off megs_b led from blue | MEGS B LED for 15 minutes; MEGS A LED for 30 minutes
| 1 | turn off megs_a led from blue
| 1 | turn on megs_b led with lamp violet level 3
| 1 | turn on megs_a led with lamp blue, level 8
| 900 | turn off megs_b led from violet | MEGS B LED for 15 minutes
| 1 | turn on megs_b led with lamp violet level 6
| 900 | turn off megs_b led from violet | MEGS B LED for 15 minutes; MEGS A LED for 30 minutes
| 1 | turn off megs_a led from blue
| 900 | move esp fltrwhl to primary | dark for 15 minutes
| 1 | move megs_a fltrwhl to primary
| 1 | move megs_b fltrwhl to primary
| 1 | move sam fltrwhl to aspect
| 900 | move esp fltrwhl to dark | Primary (except SAM) for 15 minutes
| 1 | move megs_a fltrwhl to dark
| 1 | move megs_b fltrwhl to dark
| 1 | move sam fltrwhl to dark
| 79200 | activate rts from 4 | dark for 22 hours; then trigger normal science mode. This is to allow for days between experiments (if necessary)
| 1 | set eop op_htr_trip to TBD (based on when next experiment occurs) | set EOP temp back to nominal OR to temperature for next test.
| CSTOL procedure | temp_cal_day6 (CCDs -90, EOP 15)
| Time from previous command (in seconds) | Command
| 0 | set eop op_htr_trip to 15.0c
| 86400 (Note, use same time of day for the start of this portion of the proc for all 7 experiments) | move esp fltrwhl to dark
| 1 | move megs_a fltrwhl to dark
| 1 | move megs_b fltrwhl to dark
| 1 | move sam fltrwhl to dark
| 900 | turn on megs_b led with lamp blue, level 3 | dark for 15 minutes
| 1 | turn on megs_a led with lamp blue, level 4
| 1 | enable esp cal_mode
| 1 | enable megs_p cal_mode
| 900 | turn off megs_b led from blue | MEGS B LED, ESP and MEGS P in cal mode for 15 minutes
| 1 | turn on megs_b led with lamp blue, level 6
| 1 | disable esp cal_mode
| 1 | disable megs_p cal_mode
| 900 | turn off megs_b led from blue | MEGS B LED for 15 minutes; MEGS A LED for 30 minutes
| 1 | turn off megs_a led from blue
| 1 | turn on megs_b led with lamp violet level 3
| 1 | turn on megs_a led with lamp blue, level 8
| 900 | turn off megs_b led from violet | MEGS B LED for 15 minutes
| 1 | turn on megs_b led with lamp violet level 6
| 900 | turn off megs_b led from violet | MEGS B LED for 15 minutes; MEGS A LED for 30 minutes
| 1 | turn off megs_a led from blue
| 900 | move esp fltrwhl to primary | dark for 15 minutes
| 1 | move megs_a fltrwhl to primary
| 1 | move megs_b fltrwhl to primary
| 1 | move sam fltrwhl to aspect
| 900 | move esp fltrwhl to dark | Primary (except SAM) for 15 minutes
| 1 | move megs_a fltrwhl to dark
| 1 | move megs_b fltrwhl to dark
| 1 | move sam fltrwhl to dark
| 79200 | activate rts from 4 | dark for 22 hours; then trigger normal science mode. This is to allow for days between experiments (if necessary)
| 1 | set eop op_htr_trip to 10.0c | set EOP temp back to nominal
| CSTOL procedure | temp_cal_day7 (CCDs -90, EOP 10)
| Time from previous command (in seconds) | Command
| 0 (Note, use same time of day for the start of this portion of the proc for all 7 experiments) | move esp fltrwhl to dark
| 1 | move megs_a fltrwhl to dark
| 1 | move megs_b fltrwhl to dark
| 1 | move sam fltrwhl to dark
| 900 | turn on megs_b led with lamp blue, level 3 | dark for 15 minutes
| 1 | turn on megs_a led with lamp blue, level 4
| 1 | enable esp cal_mode
| 1 | enable megs_p cal_mode
| 900 | turn off megs_b led from blue | MEGS B LED, ESP and MEGS P in cal mode for 15 minutes
| 1 | turn on megs_b led with lamp blue, level 6
| 1 | disable esp cal_mode
| 1 | disable megs_p cal_mode
| 900 | turn off megs_b led from blue | MEGS B LED for 15 minutes; MEGS A LED for 30 minutes
| 1 | turn off megs_a led from blue
| 1 | turn on megs_b led with lamp violet level 3
| 1 | turn on megs_a led with lamp blue, level 8
| 900 | turn off megs_b led from violet | MEGS B LED for 15 minutes
| 1 | turn on megs_b led with lamp violet level 6
| 900 | turn off megs_b led from violet | MEGS B LED for 15 minutes; MEGS A LED for 30 minutes
| 1 | turn off megs_a led from blue
| 900 | move esp fltrwhl to primary | dark for 15 minutes
| 1 | move megs_a fltrwhl to primary
| 1 | move megs_b fltrwhl to primary
| 1 | move sam fltrwhl to aspect
| 900 | move esp fltrwhl to dark | Primary (except SAM) for 15 minutes
| 1 | move megs_a fltrwhl to dark
| 1 | move megs_b fltrwhl to dark
| 1 | move sam fltrwhl to dark
| 79200 | activate rts from 4 | dark for 22 hours; then trigger normal science mode. This is to allow for days between experiments (if necessary)