# Revision history: 	… WP30,CB31,CB070312,WP070316, wkp3027

# Custodian:  	Charlie Barton

# Master located at:  	http://www.egy.org/Working/workingdocs.html

| # | Task | Lead person(s)/WG | Target dates | Status / Notes |
| --- | --- | --- | --- | --- |
| 501 | Ontology & VO monograph | Fox, Papitashvili, Roberts, VoiG SOC | ? | Drafted |
| 503 | eGY lead article for EOS | D Baker, Bill, Charlie | May 06 |  |
| 504 | Data paradigm article for EOS | C Barton, Ron Weaver, Roger Smith | May 06 | 1st draft completed |
| 619 | Data Website Demo | Peter Fox | Start ’06 End ‘08 | PETER TO COMPLETE IPY does this for eGY? |
| 620 | Main brochure of examples to demonstrate eGY principles | Emily | Jul 2006 | Get input from others |
| 621 | Brochure to sell eGY principles to CIO’s | Emily | Jul 2006 | 1st draft – DONE |
| 624 | Science editorial | Dan, Charlie, Emily | July 2006 | Dan to speak to Lauer (sp?) |
| 625 | Elevator presentation | C Barton, E. Hildner | July’06 | Add to Introduction.ppt |
| 629 | CAWSES VO demo | Janet Kozyra |  | In preparation. Narration needed |
| 705 | Physics Today article | Dan, Charlie | Mar 07 |  |
| 706 | Boulder-07 General Mtg | Bill, Charlie | Mar 06 | Minutes, report for EOS, IUGG |
| 707 | VoiG Conference | Peter Fox | Jun 06 | Conf & proceedings by Dec’07 |
| 708 | EGU 07 Vienna | Peter, Bernd, Mauro | Apr 07 | TH mtg for all I*Y, COSPAR, SCOR, SCAR?,WDC |
| 709 | Geoinformatics’07 San Diego | Peter | May 07 | LOC |
| 710 | Joint Assy’07 Acapulco | Bill, Ralph, … | May 07 | Booth, sessions |
| 711 | IUGG 07 Perugia | Emily, M.Kuhn | Jul 07 |  |
| 712 | Demos for Perugia | Emily, Bill, Peter | 7 Jul 07 |  |
| 713 | eGY launch, Perugia | Emily, Committee | 7 Jul 07 | Technical support issue |
|  | --Hook-up help for 7 July | Volodya, Mauro | now |  |
|  | --TG to help Emily, Perugia | ? |  |  |
|  | --Invite Samassekou 7 July | Charlie, Bob, Paul | now | Link with GIA event / CODATA |
|  | --Invite celebrity 7 July | Emily | now | ? |
|  | --Is Jeremy Sachs available? | Bob |  |  |
|  | --Is name? (IGY luminary) | Alexei |  |  |
| 714 | Fall AGU’07 | Bill, Peter, Emily, Dan | Dec 07 | Session, booth, AGU-ESSI |
|  | Ea&Sp Sci Informatics Summit | Charlie | Mar’08? | Seek agreement from key players first |
| 715 | IGC’08 Oslo | Lesley | Aug’08 |  |
| 716 | CODATA’08 Kiev | Alexei, Peter, Eric, Dave, Charlie | Sep? 08 |  |
| 717 | JA’08 AGU |  | May 08 |  |
| 718 | Fall AGU, San Francisco | Bill, Peter, Emily, Dan | Dec 08 |  |
| 719 | Boulder-8 Gen Mtg, NCAR | Peter, Charlie, eGY Team | 4-5 Mar 08 | NCAR |
| 720 | Proposal to WDC Panel | Charlie, Kathy, Peter | 28 Mar |  |
| 721 | Course in Data management | Ron Weaver, Ray Walker |  |  |
| 722 | Investigate access to private sector data | Ralph, Keith |  | Run a test case. |
| 723 | Stimulate funding for data rescue | Alexei |  |  |
|  | WDC recommendations | Jeff, Emily |  | WG report paper to be published |
| 701 | Best Practice Portal | WGBP, Eric Kihn |  | Beta version ready |
| 702 | Best Practice Demo | Eric Kihn |  |  |
|  | Best Practices article | eGY & CODATA WGs |  |  |
|  | SCID | Peter | Aug? 08 |  |
|  | SEG Leading Edge Issue | Ralph/Emily | Oct 07 |  |
|  | Share publicity with IYPE | Bill, Keith |  |  |
|  | Bring IYPE into eGY-EPO | Emily |  |  |
|  | 1-page handout template for demos | Aaron, Bill, Peter, Emily |  |  |
|  | Emergency Mngt demo | Charlie |  | GEOINSIGHT, GDIN |
|  | Press release/conference support | Emily, Bill |  |  |
|  | Proposal for Data Project to GeoUnions | Charlie, Bill , Peter | Apr’07 |  |
|  | Wind-up publication | Emily, Bill, Charlie | Dec’08 |  |
|  | Wind-up event | Emily | 31 Dec 08 | Cyber toast. eGY banner on Everest, Taj Mahal, LASP, …. |

Recommendations for WDC future

Set priority guide for data rescue. Make it public

What to do with analog data?

Quality of consistency between data holdings

….

How do we pay for ….. etc?

Become branding agency

Reduce replication between WDCs

WDCs are needed for data persistence

# Text boxes

# Action Log